## Nexus One Savings
Product Automation | [15 empty] | Regression Testing Effort Saving | [5 empty] | Functional Efforts Saving
S.Ṇo | Product | Client / Project | SIT/UAT Environment | Implementation / AMS | Automation Status (Fully Automated / Partial Automated) | Automated % | Yet to Automate % | Not Automatable % | Automation Challenges | Mitigation Options to Automate or Achieve ROI | ROI - Quality Improvement | ROI - Effort & Timeline Reduction | ROI - Cost Reduction (Resource Optimization) | Priority (P1 / P2 / P3) | Total Testcase | Automated Cases Count | Yet to Automate Cases Count | Not Automatable Cases Count | Regression Effort (Manual Testing) in days | Regression Effort indays (Automation Testing + Report Analysis) | Savings in days (ROI) | SIT Planned Efforts(in Days) | SIT Efforts taken till 22-Oct-26(in Days) | SIT Pending Efforts | No.Test cases Executed | No.Test cases Pending Executed | Pending Testcases Automated | Pending Testcases Not able to Automated | Pending Testcases - Automatable | Functional Effort (Manual Testing) in days | Functional Effort indays (Automation Testing + Report Analysis) | Functional Effort Savings in days (ROI) | ROI - Effort & Timeline Reduction
1 | Blaze PG | DU | Bank SIT |  | Partial Automated | 17.03% | 73.75% | 9.222% | CAPTCHA, OTP, MFA validations; Frequent UI changes; Unstable environment | Provide test bypass for OTP/CAPTCHA; stable automation environment; automation-ready UI standards | +25% defect detection | 86.49% | 2 QA FTE equivalent | P1 | 6506 | 1108 | 4798 | 600 | 74 | 10 | 64
2 | PG | Ecentric | FSS SIT |  | Partial Automated | 54.55% | 34.18% | 11.28% | Logs, DB validation is not possible because of access related to access logs. | Logs and DB access to be provided in SIT env |  | 75% | 9 days saved per regression cycle | P1 | 3520 | 1920 | 1203 | 397 | 12 | 3 | 9
3 | PG | Al-Rajhi | Bank UAT |  | Partial Automated | 2.446% | 74.41% | 23.14% | Logs, DB and Applepay, Samsung pay and SDK automation is not possible because it can be accessable in UAT environment only | Logs, DB and Whitelist URLs for Applepay and samsung pay, enable automation access in VDI. | +40% defect detection | 73.33% | 11 days saved per regression cycle | P1 | 3025 | 74 | 2251 | 700 | 15 | 4 | 11
4 | PG | Neoleap | Bank UAT |  | Partial Automated | 0% | 0% | 100% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 77.78% | 14 days saved per regression cycle | P1 | 8466 | 0 | 0 | 8466 | 18 | 4 | 14
5 | PG | KNET | FSS SIT |  | Not able to Automate | 0.4912% | 94.6% | 4.912% | No frequent releases currently |  |  | 71.43% | 1 QA FTE equivalent | P2 | 2036 | 10 | 1926 | 100 | 14 | 4 | 10
6 | PG | Pinelabs-ENBD | Bank UAT |  | Partial Automated | 8.679% | 64.37% | 26.95% | Applepay, Samsung pay and SDK automation is not possible because it can be accessable in UAT environment only | Whitelist URLs for Applepay and samsung pay, enable automation access in VDI. | +50% defect detection | 73.33% | 11 days saved per regression cycle | P1 | 1855 | 161 | 1194 | 500 | 15 | 4 | 11
7 | PG | Pinelabs-WIO | Bank UAT |  | Partial Automated | 10.9% | 72.47% | 16.62% | Applepay, Samsung pay and SDK automation is not possible because it can be accessable in UAT environment only | Whitelist URLs for Applepay and samsung pay, enable automation access in VDI. | +50% defect detection | 73.33% | 11 days saved per regression cycle | P1 | 3008 | 328 | 2180 | 500 | 15 | 4 | 11
8 | PG | FAB | BANK UAT |  | Partial Automated | 18.07% | 77.01% | 4.912% | OTP, Wallet Transactions, QR and Portal Inside VDI | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 75% | 1 QA FTE equivalent | P1 | 2036 | 368 | 1568 | 100 | 24 | 6 | 18
9 | PG | OAB | FSS SIT |  | Partial Automated | 13.66% | 82.39% | 3.948% | CAPTCHA & OTP | Provide OTP/CAPTCHA bypass and stable automation-ready environment | +45% defect detection | 75% | 8 days saved per regression cycle | P1 | 2533 | 346 | 2087 | 100 | 16 | 4 | 12
10 | PG | NBO | BANK SIT |  | Not able to Automate | 0.2369% | 4.224% | 95.54% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +50% defect detection | 66.67% | 5 days saved per regression cycle | P1 | 2533 | 6 | 107 | 2420 | 12 | 4 | 8
11 | Blaze CMS | SBI | FSS SIT | Implementation | Partial Automated | 13.73% | 66.06% | 20.21% | We need to fetch data from DCMS 1.0(Monolith) to microservice that integration is not availble at SIT and some external services integration is not available at SIT | By using Mock we can cover sanity |  | 33.33% |  | P1 | 9897 | 1359 | 6538 | 2000 | 30 | 20 | 10 | 60 | 10 | 50 | 5200 | 4697 | 8538 | 2000 | 6538 | 30 | 20 | 10 | 30%
12 | Blaze CMS | Kotak | FSS SIT | Implementation | Partial Automated | 42.86% | 56.34% | 0.8021% | Environment is not available, Project is in On-hold status |  |  | 0% |  |  | 3740 | 1603 | 2107 | 30 | 15 | 15 | 0 | 100 | 60 | 40 | 2740 | 1000 | 0 | 150 | 850 | 10 | 5 | 5 | 50%
13 | Blaze CMS | CBI | FSS SIT | AMS | Partial Automated | 0% | 100% | 0% | We had delivered this project very short period so we did not automate due to bandwidth unavailability |  |  | 0% |  |  | 1529 | 0 | 1529 | 0 | 10 | 10 | 0
15 | Blaze CMS | PSB | FSS SIT | AMS | Partial Automated | 0% | 100% |  | We had delivered this project very short period so we did not automate due to bandwidth unavailability |  |  | #DIV/0! |  |  | 1387 | 0 | 1387 | 0 |  |  | 0
16 | MAPS | QNB | Bank SIT |  | Partial Automated | 9.697% | 61.16% | 29.14% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 60% |  | P1 | 6404 | 621 | 3917 | 1866 | 15 | 6 | 9
17 | MAPS | SADAD | Bank SIT |  | Partial Automated | 6.389% | 91.3% | 2.315% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 57.14% |  | P1 | 2160 | 138 | 1972 | 50 | 7 | 3 | 4
18 | Recon | Indian Bank(IMPS and UPI) | FSS SIT | Implementation | Partial Automated | 9.239% | 86.23% | 4.529% | Skip SIT |  |  | 40% |  | P1 | 5520 | 510 | 4760 | 250 | 20 | 12 | 8
19 | Recon | HDFC | Bank SIT | Implementation | Partial Automated | 14.49% | 45.57% | 39.95% | SIT is carried out in Bank SIT Environment |  | 60% | 33.33% |  | P1 | 3755 | 544 | 1711 | 1500 | 15 | 10 | 5
20 | Recon | Kotak | FSS SIT | Implementation | Partial Automated | 7.078% | 65.16% | 27.76% |  |  |  | 21.74% |  | P1 | 7205 | 510 | 4695 | 2000 | 23 | 18 | 5
21 | Recon | IDFC | FSS SIT | AMS | Partial Automated | 2.674% | 82.62% | 14.71% |  |  |  | 46.67% |  | P2 | 3740 | 100 | 3090 | 550 | 15 | 8 | 7
22 | Recon | Airtel | FSS SIT | AMS | Partial Automated | 1.744% | 95.12% | 3.139% |  |  |  | 41.67% |  | P2 | 2867 | 50 | 2727 | 90 | 12 | 7 | 5
23 | Recon | IPPB | FSS SIT | Implementation | Partial Automated | 9.38% | 84.85% | 5.772% |  |  |  | 46.67% |  | P2 | 3465 | 325 | 2940 | 200 | 15 | 8 | 7
24 | Recon | Bandhan Bank | FSS SIT | AMS | Partial Automated | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | #DIV/0! |  | P2 |  |  | 0 |  |  |  | 0
25 | Recon | BFL | FSS SIT | AMS | Partial Automated | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | #DIV/0! |  | P2 |  |  | 0 |  |  |  | 0
26 | Recon | Ujjivan Bank | FSS SIT | AMS | Partial Automated | #DIV/0! | #DIV/0! | #DIV/0! |  |  |  | #DIV/0! |  | P2 |  |  | 0 |  |  |  | 0
| Recon | NI_Settlement | Bank UAT | Implementation | Partial Automated | 37.9% | 12.73% | 49.37% |  |  |  | 51.92% |  | P1 | 25319 | 9595 | 3224 | 12500 | 52 | 25 | 27
| Recon | NI_Recon | Bank UAT | Implementation | Partial Automated | 0% | 43.55% | 56.45% |  |  |  | 55.56% |  | P1 | 18600 | 0 | 8100 | 10500 | 45 | 20 | 25
37 | Recon | NI_ChargeBack | Bank UAT | Implementation | Partial Automated | 0% | 0% | 100% | SIT is carried out in Bank UAT Environment |  |  | 0% |  | P1 | 27410 | 0 | 0 | 27410 | 32 | 32 | 0
39 | Recon | ADCB | Bank UAT | Implementation | Partial Automated | 0% | 0% | 100% | SIT is carried out in Bank UAT Environment |  |  | 0% |  | P1 | 1312 | 0 | 0 | 1312 | 10 | 10 | 0
40 | Recon | QNB Alhali | FSS SIT | Implementation | Partial Automated | 0% | 83.27% | 16.73% |  |  |  | 42.86% |  | P1 | 2690 | 0 | 2240 | 450 | 14 | 8 | 6
41 | CMS | SBI PCMS | Bank Onsite SIT | AMS | Partial Automated | 0% | 0% | 100% | SIT has been carried out in the Client environment | FSS SIT Environment to be created with external dependencies addressed |  | 0% |  | P1 | 2057 | 0 | 0 | 2057 | 9 | 9 | 0
42 | CMS | SBI DCMS | Bank Onsite SIT | AMS | Partial Automated | 0% | 0% | 100% | SIT has been carried out in the Client environment | FSS SIT Environment to be created with external dependencies addressed |  | 0% |  | P1 | 2422 | 0 | 0 | 2422 | 9 | 9 | 0
43 | CMS | UJJIVAN | FSS SIT | AMS | Partial Automated | 82% | 8% | 10% |  |  |  | 30% |  | P2 | 7880 | 6462 | 630 | 788 | 20 | 14 | 6
44 | CMS | BFL | FSS SIT | AMS | Partial Automated | 30% | 48% | 22% |  |  |  | 30% |  | P2 | 8831 | 2649 | 4239 | 1943 | 20 | 14 | 6
45 | CMS | IDFC | FSS SIT | AMS | Partial Automated | 80% | 6% | 14% |  |  |  | 40% |  | P1 | 11827 | 9462 | 710 | 1656 | 35 | 21 | 14
46 | CMS | CGGB | FSS SIT | AMS | Partial Automated | 75% | 0% | 25% |  |  |  | 73.33% |  | P3 | 7880 | 5910 | 0 | 1970 | 15 | 4 | 11
47 | CMS | ALAnsari | FSS UAT | AMS | Partial Automated | 65% | 10% | 25% | Testing is performed through RDP access to the jump server, resulting in limited accessibility and reduced testing efficiency. | Need to establish direct access to the UAT application to improve testing efficiency and support automation activities. | +40% defect detection | 75% |  | P2 | 2321 | 1509 | 232 | 580 | 20 | 5 | 15
48 | CMS | Sharaf | FSS UAT | AMS | Partial Automated | 0% | 65% | 35% | Testing is performed through RDP access to the jump server, resulting in limited accessibility and reduced testing efficiency. | Need to establish direct access to the UAT application to improve testing efficiency and support automation activities. | +45% defect detection | 71.43% |  | P3 | 5501 | 0 | 3576 | 1925 | 14 | 4 | 10
49 | CMS | Comera Pay | FSS UAT | AMS | Partial Automated | 0% | 75% | 25% | Testing is performed through RDP access to the jump server, resulting in limited accessibility and reduced testing efficiency. | Need to establish direct access to the UAT application to improve testing efficiency and support automation activities. | +40% defect detection | 72.22% |  | P2 | 4131 | 0 | 3098 | 1033 | 18 | 5 | 13
50 | CMS | ICICI DCMS | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | SIT has been carried out in the Client environment | FSS SIT Environment to be created with external dependencies addressed | +45% defect detection | 0% |  | P3 | 1867 | 0 | 0 | 1867 | 20 | 20 | 0
51 | CMS | ICICI PCMS | FSS SIT | AMS | Partial Automated | 0% | 60% | 40% | Limited automation coverage in SIT due to unavailable external dependencies. | Create a dedicated test environment with all required external dependencies integrated to enable end-to-end automation. | +40% defect detection | 84% |  | P3 | 3072 | 0 | 1843 | 1229 | 25 | 4 | 21
52 | CMS | IndusInd | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | SIT has been carried out in the Client environment | FSS SIT Environment to be created with external dependencies addressed | +40% defect detection | 0% |  | P3 | 1812 | 0 | 0 | 1812 | 20 | 20 | 0
53 | CMS | Kotak | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 0% |  | P3 | 1110 | 0 | 0 | 1110 | 19 | 19 | 0
54 | CMS | BOB | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | SIT has been carried out in the Client environment | FSS SIT Environment to be created with external dependencies addressed | +45% defect detection | 0% |  | P3 | 6711 | 0 | 0 | 6711 | 27 | 27 | 0
55 | CMS | HDFC | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | BANK VDI Inside Bank SIT(Automation tools cannot access applications directly due to network restrictions.) | Whitelist URLs, provide OTP bypass, enable automation access in VDI. | +40% defect detection | 0% |  | P2 | 6541 | 0 | 0 | 6541 | 34 | 34 | 0
56 | TMS | SAMA | Bank SIT | AMS | Not able to Automate | 0% | 0% | 100% | Bank VDI Environment as there are external Dependence | Whitelist URLs, provide OTP bypass, enable automation access in VDI. |  | 75% |  | P1 | 5200 | 0 | 0 | 5200 | 20 | 5 | 15

## Pipeline CR's
Product Details |  |  |  | 2026-11-01 |  |  |  |  | 2026-12-01
S.Ṇo | Product | Client / Project | SIT/UAT Environment | CR's Count | CR Manual Efforts | CR Automation Efforts | Savings | ROI | CR's Count | CR Manual Efforts | CR Automation Efforts | Savings | ROI
1 | Blaze PG | DU | Bank SIT
2 | PG | Ecentric | FSS SIT
3 | PG | Al-Rajhi | Bank UAT
4 | PG | Neoleap | Bank UAT
5 | PG | KNET | FSS SIT | 0 | 0 | 0 | 0 |  |  | 0 | 0
6 | PG | Pinelabs-ENBD | Bank UAT
7 | PG | Pinelabs-WIO | Bank UAT
8 | PG | FAB | BANK UAT | 6 | 180 |  |  |  |  | 2 | 60
9 | PG | OAB | FSS SIT | 1 | 24 |  |  |  |  | 2 | 40
10 | PG | NBO | BANK SIT | 1 | 10 | 0 | 0 |  |  | 2 | 24
11 | Blaze CMS | SBI | FSS SIT
12 | Blaze CMS | Kotak | FSS SIT | 3 | 30 | 20 | 10 | 33.33%
13 | Blaze CMS | CBI | FSS SIT |  |  |  | 0 | #DIV/0!
14 | Blaze CMS | KVB | FSS SIT |  |  |  | 0 | #DIV/0!
15 | Blaze CMS | PSB | FSS SIT |  |  |  | 0 | #DIV/0!
16 | MAPS | QNB | Bank SIT |  |  |  | 0 | #DIV/0!
17 | MAPS | SADAD | Bank SIT |  |  |  | 0 | #DIV/0!
18 | Recon | Indian Bank(IMPS and UPI) | FSS SIT |  |  |  | 0 | #DIV/0!
19 | Recon | HDFC | Bank SIT |  |  |  | 0 | #DIV/0!
20 | Recon | Kotak | FSS SIT |  |  |  | 0 | #DIV/0!
21 | Recon | IDFC | FSS SIT |  |  |  | 0 | #DIV/0!
22 | Recon | Airtel | FSS SIT |  |  |  | 0 | #DIV/0!
23 | Recon | IPPB | FSS SIT |  |  |  | 0 | #DIV/0!
24 | Recon | Bandhan Bank | FSS SIT |  |  |  | 0 | #DIV/0!
25 | Recon | BFL | FSS SIT |  |  |  | 0 | #DIV/0!
26 | Recon | Ujjivan Bank | FSS SIT |  |  |  | 0 | #DIV/0!
| Recon | NI_Settlement | Bank UAT | 51 | 122 | 60 | 62 | 50.82%
| Recon | NI_Recon | Bank UAT | 3 | 9 | 9 | 0 | 0%
37 | Recon | NI_ChargeBack | Bank UAT | 3 | 53 | 53 | 0 | 0% | 2 | 56 | 56 | 0 | 0%
39 | Recon | ADCB | Bank UAT |  |  |  | 0 | #DIV/0!
40 | Recon | QNB Alhali | FSS SIT |  |  |  | 0 | #DIV/0!
41 | CMS | SBI PCMS | Bank Onsite SIT |  |  |  | 0 | #DIV/0!
42 | CMS | SBI DCMS | Bank Onsite SIT |  |  |  | 0 | #DIV/0!
43 | CMS | UJJIVAN | FSS SIT |  |  |  | 0 | #DIV/0!
44 | CMS | BFL | FSS SIT |  |  |  | 0 | #DIV/0!
45 | CMS | IDFC | FSS SIT |  |  |  | 0 | #DIV/0!
46 | CMS | CGGB | FSS SIT |  |  |  | 0 | #DIV/0!
47 | CMS | ALAnsari | FSS UAT |  |  |  | 0 | #DIV/0!
48 | CMS | Sharaf | FSS UAT |  |  |  | 0 | #DIV/0!
49 | CMS | Comera Pay | FSS UAT |  |  |  | 0 | #DIV/0!
50 | CMS | ICICI DCMS | Bank SIT |  |  |  | 0
51 | CMS | ICICI PCMS | FSS SIT |  |  |  | 0
52 | CMS | IndusInd | Bank SIT |  |  |  | 0
53 | CMS | Kotak | Bank SIT |  |  |  | 0
54 | CMS | BOB | Bank SIT |  |  |  | 0
55 | CMS | HDFC | Bank SIT
56 | TMS | SAMA | Bank SIT

## Common Automation Challenges
Common Automation Challenges
CAPTCHA / OTP restrictions
Multi-factor authentication (MFA)
Frequent UI changes
Dynamic object identifiers
Third-party integrations
Environment instability
Test data dependency
Delayed deployments
Frequent requirement changes
Legacy technologies
File upload/download validations
PDF/Image validation
Limited API availability
Vendor/Bank dependency
Short release cycles
Absence of dedicated automation environment